## Sheet1
Task | Person in Charge | Start Date | End Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Finance |  | 2024-11-01 | 2024-11-19
Monthly Budget Planning | Finance Manager | 2024-11-01 | 2024-11-01
Payroll Processing | Payroll Officer | 2024-11-06 | 2024-11-06
Financial Report Generation | Accountant | 2024-11-07 | 2024-11-07
Mid-Month Budget Check | Finance Manager | 2024-11-08 | 2024-11-09
Vendor Invoice Processing | Accounts Payable Clerk | 2024-11-13 | 2024-11-13
Monthly Report Preparation | Data Analyst | 2024-11-18 | 2024-11-19
Human Resources |  | 2024-11-01 | 2024-11-14
Employee Attendance Review | HR Coordinator | 2024-11-01 | 2024-11-03
Update Employee Training Records | HR Assistant | 2024-11-02 | 2024-11-02
Safety Training Refresher | HR & Safety Officer | 2024-11-09 | 2024-11-09
New Employee Orientation (if needed) | HR Manager | 2024-11-10 | 2024-11-12
Team Development Training | HR Coordinator | 2024-11-14 | 2024-11-14
Maintenance |  | 2024-11-03 | 2024-11-27
Office Cleaning and Disinfection | Facility Manager | 2024-11-03 | 2024-11-03
Fire Safety Equipment Check | Safety Officer | 2024-11-04 | 2024-11-04
Equipment Repair Requests | Maintenance Supervisor | 2024-11-12 | 2024-11-13
Equipment Calibration | Maintenance Team | 2024-11-21 | 2024-11-22
Fire Drill (Quarterly) | Safety Officer | 2024-11-26 | 2024-11-26
Building Maintenance | Facility Manager | 2024-11-27 | 2024-11-27
IT & Security |  | 2024-11-01 | 2024-11-30
System Backups | IT Specialist | 2024-11-01 | 2024-11-02
Workstation Setup & Maintenance | IT Support | 2024-11-05 | 2024-11-06
Website Updates & Content Review | IT & Marketing Teams | 2024-11-17 | 2024-11-17
IT Security Check | IT Security Specialist | 2024-11-18 | 2024-11-18
Database Clean-Up | IT Data Analyst | 2024-11-25 | 2024-11-30